## Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 27 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete
Main Milestone | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Loading Data (incl. API) | 1 | 1 |  |  | 0%
Data Merging | 2 | 1 |  |  | 0%
Data Exploring + Missings | 3 | 2 |  |  | 0%
Research on Models, writing context, hypothesis etc | 5 | 2 |  |  | 0%
Study + Exams + Holiday + Block Weeks Deadlines (no thesis) | 7 | 8 |  |  | 0%
Running Models | 15 | 2 |  |  | 0%
Math Model Interpreation | 17 | 2 |  |  | 0%
Domain Model Interpretation | 19 | 1 |  |  | 0%
Placing in Context | 20 | 1 |  |  | 0%
Week Off + Hand to Friend | 21 | 1 |  |  | 0%
Any remaining Edits, Robustness Checks | 22 | 5 |  |  | 0%
Activity 12 |  |  |  |  | 0%
Activity 13 |  |  |  |  | 0%
Activity 14 |  |  |  |  | 0%
Activity 15 |  |  |  |  | 0%
Activity 16 |  |  |  |  | 0%
Activity 17 |  |  |  |  | 0%
Activity 18 |  |  |  |  | 0%
Activity 19 |  |  |  |  | 0%
Activity 20 |  |  |  |  | 0%
Activity 21 |  |  |  |  | 0%
Activity 22 |  |  |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 5%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%